## Sheet1
No. | Page Name | Page URI | Static HTML | Status | HTML Demo |  | Số thứ tự | Người làm | Thời gian của task 1h = 5.5 usd tổng thời gian là 152h = 19228000 tr
1 | Home (Guest) | / |  | HTML | https://newligion.com/index.html |  | 4 | Sử | 16
2 | Sign In | /sign-in |  | HTML | MODAL |  | 2 | Phuong | 5
3 | Forgot Password | /forgot-password |  | HTML | MODAL |  | 2 | Phuong | 5
4 | Forgot Password::Change new Password | /forgot-password/change |  | HTML | MODAL | chưa | 2 | Phuong | 5 |  | đã làm
5 | Forgot Password::Verify Code | /forgot-password/verify |  | HTML | MODAL | chưa | 2 | Phuong | 5 |  | chưa có thông tin
6 | Sign Up | /sign-up |  | HTML | MODAL |  | 2 | Phuong | 5 |  | hiển thị static
7 | Sign Up::Verify | /sign-up/verify |  |  | MODAL | chưa | 2 | Phuong | 5 |  | chưa làm
8 | Sign Up::Complete Profile | /sign-up/complete-profile |  | HTML | https://newligion.com/personal_profile.html |  | 2 | Phuong | 5 |  | phần quan trọng
9 | About Us | /about-us | 〇 | HTML |  | Hiển thị static | 1 | Phuong | 0.5
10 | Terms of Services | /terms | 〇 | HTML |  |  | 1 | Phuong | 0.5 | Phase 1( 1 tháng ): HTML với thực hiện hành đông cơ bản của trang
11 | Privacy | /privacy | 〇 | HTML |  |  | 1 | Phuong | 0.5 | Phase 1.1( 1 tháng): Thực hiện các chức năng, flow yêu cầu và xử lý data từ API
12 | Program Policies | /program-policies | 〇 | HTML |  |  | 1 | Phuong | 0.5
13 | User Agreement | /user-agreement | 〇 | HTML |  |  | 1 | Phuong | 0.5
14 | Directory | /directory |  |  |  |  | ? | Phuong | 4
15 | Message | /messages |  |  |  |  | ? | Phuong | 4
16 | Profile | /profile |  |  |  |  | 3 | Phuong | 4
17 | Create an NRM profile | /create-religion |  | HTML | step1: https://newligion.com/please-read |  | 8 | Phuong | 4
[5 empty] | step2: https://newligion.com/basic-profile |  | 8 | Phuong | 4
[5 empty] | step3: https://newligion.com/congratulations |  | 8 | Phuong | 4
18 | Writing | /writing |  | HTML | https://newligion.com/writings |  | 6 | Sử | 26
19 | Lounge (Home for Member) | /lounge |  | HTML | https://newligion.com/lounge |  | 5 | Phuong | 26
20 | NRM Detail | /religion/{id} |  | HTML |  |  | 8 | Phuong | 6.5
21 | Member (Profile) Detail | /member/{id} |  | HTML |  |  | 3 | Sử | 7.5
22 | Book Detail | /book/{id} |  | HTML |  |  | 7 | Sử | 8
23 | Set Membership | /set-membership |  |  | https://newligion.com/create-default |  | x | Sử | 0.5
152
Link : https://www.figma.com/file/u5Yk2YgrPb71oLyxqBNm1I/NRM?node-id=0%3A1

## SignIn
This modal open from Footer > Join / SignIn
API Usage | signIn
After login, redirect to /lounge page
username
password

## SignUp
|  | SignUp Flow | Step1: Enter email
Step2: Enter username & password
Step3: Verification & auto SignIn
Step4: Update more profile info
Step1: Enter email
|  |  |  | API Usage signUpValidateEmail | signUpValidateEmail
After submit OK, next to Step2 modal
Step2: Enter username, password
API Usage signUp
After submit OK, next to Step3 modal
Step3: Verification
Verification code |  |  |  | API Usage signUpConfirm
After submit OK, auto signIn and redirect to /personal-profile page
Confirm
Step4: Update more profile info
API Usage updateAccount
After submit OK, auto signIn and redirect to /account/complete-profile
email
username
password
do later
please add save button here
phone
remove password fileds